# Project Risk Management

Risk management is the systematic process of identifying, analyzing and responding to potential project risk. It includes maximizing the probability and impact of positive events and minimizing the probability and consequences of events adverse to project objectives. Figure 11.1 provides an overview of the following major processes.

11.1 Risk Management Planning—deciding how to approach and plan the risk management activities for a project.

11.2 Risk Identification—determining which risks might affect the project and documenting their characteristics.

11.3 Qualitative Risk Analysis—performing a qualitative analysis of risks and conditions to prioritize their effects on project objectives.

11.4 Quantitative Risk Analysis—measuring the probability and impact of risks and estimating their implications for project objectives.

11.5 Risk Response Planning—developing procedures and techniques to enhance opportunities and to reduce threats to the project’s objectives.

11.6 Risk Monitoring and Control—monitoring residual risks, identifying new risks, executing risk reduction plans and evaluating their effectiveness through the project life cycle.

{Note to insert chart with processes with inputs, tools & techniques, outputs like pg 112 of the PMBOK Guide, 1996}

These processes interact with each other and with the processes in the other knowledge areas. Each process generally occurs at least once in every project. Although processes are presented here as discrete elements with well-defined interfaces, in practice they may overlap and interact in ways not detailed here. Process interactions are discussed in detail in Chapter 3.

Project risk is an uncertain event or condition that, if it occurs, has a positive or negative effect on a project objective.  A risk has a cause and, if it occurs, an impact.  For example, the cause may be requiring a permit or having limited personnel assigned to the project.  The risk event is that the permit may take longer than planned or the personnel may not be adequate for the task.  If either of these uncertain events occurs, there will be an impact on the project cost, schedule or quality. Risk conditions include practices or aspects of the project environment that may make contribute to project risk such as a lack of project scheduling personnel or inability to make decisions in a timely fashion.

Project risk includes both threats to the project’s objectives and opportunities to improve on those objectives.  It has its origins in the uncertainty that is present in all projects. Risks may be known unknowns; risks that are identified, assessed and quantified and for which plans can be made.  Risks may be unknown unknowns; risks that are not yet identified or are impossible to predict. Although specific risks or conditions are not identified, project managers know from past experience that a general level of risk can be expected.

Risk should be related to reward. Risks accepted should be in balance with the reward that may be gained by taking the risk.  For example, a fast-track schedule is a risk taken to achieve the benefit of a shortened schedule.

To be successful, the organization must be committed to addressing risk management seriously throughout the project.  One measure of the organizational commitment is its dedication to gathering high-quality and honest data on project risks and their characteristics.

11.1 Risk Management Planning

Risk management planning is the process of deciding how to approach and plan the risk management activities for a project. It is important to plan for the risk management processes that follow to ensure that the level, type, and visibility of risk management are commensurate with both the risk and importance of the project to the organization.

11.1.1 Inputs to Risk Management Planning

.1 Project charter.  The project charter is discussed in section 5.1.3.1.  It includes the business needs and project description at a level appropriate to the needs of the project.

.2 Organization's risk management policies. Some organizations may have predefined methods for qualitative and quantitative risk analysis.

.3 Defined roles and responsibilities. Predefined roles, responsibilities and authority levels for decision-making will influence planning.

.4 Stakeholder risk tolerances. Different organizations and different individuals have different tolerances for risk.  These may be expressed in policy statements or revealed in actions.

.5 Template for the organization’s risk management  plan.  A pro-forma standard that the organization has developed for risk management generally.  That standard must be adapted to each project by the project manager or the risk management team.   It should be improved based on experience from each project.

.7 Work breakdown structure.  The WBS is described in section 5.3.3.1.

11.1.2 Tools and Techniques for Risk Management Planning

.1 Planning meetings.  These are designed to adapt the risk management plan template to the current project.  Attendees include the project manager, the project team leaders, anyone in the organization with responsibility to manage the risk planning and execution activities, key stakeholders and others as needed.

11.1.3 Outputs from Risk Management Planning

.1 Risk management plan.   The risk management plan documents how risk identification, assessment, quantification, response planning, monitoring and control will be structured and performed during the project life cycle. The risk management plan does not address responses to individual risks – this is accomplished in the risk response plan that is discussed in section 11.5.3.  The risk management plan may include:

- .Methodology. defines theapproaches, tools and data sources that may be used to perform risk management on this project.

- Roles and responsibilities.  Defines the lead, support and risk management team membership for each type of action in the risk management  plan. Risk management teams organized outside of the project office may be able to perform more independent, unbiased risk analyses of projects than those from the sponsoring project team.

- Timing. Defines how often the risk management process will be performed through the project life cycle. Results should be developed early enough to affect decisions.  The decisions should be revisited periodically during project execution.

- Scoring and interpretation. The scoring and interpretation methods appropriate for the type and timing of the qualitative and quantitative risk analysis being performed. Methods and scoring must be determined in advance to ensure consistency.

- Thresholds. The threshold criteria for risks that will be acted upon, by whom and in what manner. The project customer or originator may have a different risk threshold from the providing organization. The acceptable threshold forms the target against which the project team will measure the effectiveness of the risk response plan execution.

- Reporting formats. Describes the content and format of the risk response plan described in Section 11.5.3. Defines how the results of the risk management processes will be documented, analyzed and communicated to the project team, internal and external stakeholders, sponsors and others.

- Tracking. Documents how all facets of risk activities will be recorded for the benefit of the current project, future needs and lessons learned. Documents if and how risk processes will be audited.

# 11.2 Risk Identification

Risk identification involves determining what risks might affect the project and documenting their characteristics. Participants in risk identification should include as many of the following as possible: project team, risk management team, subject matter experts from other parts of the company, customers, end users, other project managers, stakeholders, and outside experts.

Risk identification is an iterative process. The first iteration may be performed by a part of the project team, or by the risk management team. The entire project team and primary stakeholders may make a second iteration. To achieve an unbiased analysis, persons who are not involved in the project may perform the final iteration.

11.2.1.	Inputs to Risk Identification

.1 Risk management plan. This plan is described in 11.1.3.

.2 Project planning outputs. Risk identification requires an understanding of the project's mission, scope, and objectives of the owner, sponsor or stakeholders. Outputs of other processes should be reviewed to identify possible risks. These may include:

- Project charter.

- Work breakdown structure.

- Product description.

- Project schedule logic.

- Cost and duration estimates.

- Resource plan.

- Procurement plan.

- Assumptions list.

- Constraints list.

.3 Risk categories. Risk categories help to organize and identify possible risks that may affect the project for better or worse. Categories should be well defined and reflect common sources of risk for the industry or application area. Commonly used categories include:

- Technical, quality or performance risks—such as reliance on unproven or complex technology or a requirement to achieve unrealistic performance goals, changes to the technology used or to industry standards.

- Project-management risks—such as poor allocation of time and resources, inadequate quality of the project plan, poor use of project management disciplines, unrealistic or incomplete estimates, problems with suppliers and subcontractors, poor communication techniques and inability to make project decisions.

- Organization risks—such as cost, time and scope objectives that are internally inconsistent, lack of prioritization of projects, inadequacy or interruption of funding, funding interruptions and resource conflicts with other projects in the organization.

- External risks—such as shifting legal or regulatory environment, changes in marketplace trends, labor issues, sponsor or owner issues, country risk and weather, and physical risks for which plans can be developed. Some extreme events such as earthquakes, floods, and civil unrestare generally considered disaster recovery scenarios rather than project risks.

.4 Historical information. Information on prior projects may be available from the following sources:

- Project files—one or more of the organizations involved in the project may maintain records of previous project results that can be used to identify risks. These may be final project reports or risk response plans.  They may include lessons learned that describe problems and their resolutions. Project team knowledge may be unorganized but available through the experience of the project stakeholders or others in the organization.

- Published information–commercial databases, academic studies, benchmarking and other published studies may be available for many application areas.

11.2.2.	Tools and Techniques for Risk Identification

.1 Documentation reviews. Performing a structured review of project plans and assumptions, prior project files and other information is generally the initial step taken by project teams.

.2 Information gathering techniques. Brainstorming, the Delphi technique and interviewing are used in risk identification.

- Brainstorming.  Brainstorming is probably the most frequently used risk identification technique. The goal is to obtain a comprehensive list of risks that can be addressed later in the qualitative and quantitative risk analysis processes.

Using brainstorming, a meeting is organized with a multidisciplinary set of experts.  Under the leadership of a facilitator, these people generate ideas about project risk.  The brainstorming meeting proceeds without interruption, without expressing judgment or criticism of others’ ideas and without regard to individuals’ status in the organization.   Sources of risk are identified in broad scope and posted for all to examine during the meeting.  Risks are then categorized by type of risk and their definitions are sharpened.  Brainstorming can be more effective if participants prepare in advance, the facilitator develops some risks in advance, and the meeting is structured by project segment and risk category.

- Delphi technique.  The Delphi technique is a way to reach a consensus of experts on a subject such as proejct risk.  Project risk experts are identified but participate anonymously.  They do not meet face-to-face.

A facilitator uses a questionnaire to solicit ideas about the important project risks.  The responses are submitted and put into risk categories by the facilitator.  These risks are then circulated to the experts for further comment.  Consensus on the main project risks may be reached in a few rounds of this process.  The Delphi technique helps reduce bias in the and keeps any person from having undue influence on the outcome.

- Interviewing.  Risks can be identified by interviews of experienced project managers or subject matter experts.  The person responsible for risk identification identifies the appropriate individuals, briefs them on the project, provides information such as the work breakdown structure and the  list of assumptions.  The interviewees identify risks on the project based on their experience, project information and other sources they find useful.

- Strengths, weaknesses, opportunities and threats (SWOT) analysis.  Ensures examination of the project from each of the SWOT perspectives to increase the breadth of the risks considered.

- .4 Assumptions analysis.  Every project is conceived and developed based on a set of hypotheses, scenarios or assumptions.  Assumptions analysis is a technique that explores the assumptions’ accuracy.  It identifies risks to the project from inaccuracy, inconsistency or incompleteness of assumptions

.5 Diagramming techniques. Diagramming techniques may include:

- Cause-and-effect diagrams (also known as Ishikawa or fishbone diagrams)-useful for identifying causes of risks (described in section 8.1.2.3).

- System or process flowcharts—show how various elements of a system interrelate and the mechanism of causation (described in section 8.1.2.3).

- Influence diagrams—a graphical representation of a problem showing causal influences, time ordering of events and other relationships among variables and outcomes.

11.2.3	Outputs from Risk Identification

.1 Identified risks . Risks are discrete occurrences or conditions that may affect the project for better or worse.

.2 Triggers. Triggers, sometimes called risk symptoms or warning signs, are indications that a risk has occurred or is about to occur. For example, failure to meet intermediate milestones may be an early warning signal of an impending schedule delay.

.3 Inputs to other processes. Risk identification may identify a need for further action in another area. For example, the work breakdown structure may not have sufficient detail to allow adequate identification of risks, or the schedule may not be complete or entirely logical.

11.3 Qualitative Risk Analysis

Qualitative risk analysis is the process of performing a qualitative analysis of identified risks. This process is intended to prioritize risks according to their potential effect on project objectives.  Qualitative risk analysis is one way of determining the importance of addressing specific risks and guides risk response measures. The time-criticality of risk-related actions may magnify the importance of a risk. An evaluation of the quality of the available information also helps modify the assessment of the risk. Qualitative risk Analysis requires that the probability and impact of the risks be estimated using qualitative analysis methods and tools. Using these tools helps correct biases that are often present in a project plan.  Qualitative risk analysis should be revisited during the project’s life cycle to stay current with changes in project risks.  This process can lead to further analysis in quantitative risk analysis (11.4) or directly to risk response planning (11.5).

11.3.1 Inputs to Qualitative Risk Analysis

.1 Risk management plan. This plan is described in 11.1.3.

.2 Identified risks. Risks discovered during the risk identification process are evaluated along with their potential impacts on the project.

.3 Project status. The uncertainty of a risk often depends on the project’s progress through its life cycle. Early in the project many risks have not surfaced, the design for the project is immature and changes can occur, making it likely that more risks will be discovered.

.4 Project type. Projects of a common or recurrent type tend to have less risk. Projects using state-of-the-art  or first-of-a-kind technology  or highly complex projects tend to have more risk.

.5 Data precision. Precision describes the extent to which a risk is known and understood. It measures the extent of data available as well as the reliability of data. The source of the data that was used to identify the risk must be evaluated.

.6 Scales of probability and impact.  These scales are to be used in assessing the two key dimensions of risk, described in 11.3.2.2.

11.3.2 Tools and Techniques for qualitative Risk Analysis

.1 Risk probability and impact. Risk probability and risk impact may be described in qualitative terms such as very high, high, moderate, low and very low.

- Risk probability is the likelihood that a risk will occur.

- Risk impact is the effect on project objectives if the risk occurs.

These two dimensions of risk are applied to specific risks, not to the overall project.  Analysis of risks using probability and impact helps identify those risks that should be managed aggressively.

##### .2 Probability / impact risk rating matrix. A matrix may be constructed that assigns risk ratings (low, moderate and high) to risks or conditions based on combining probability and impact scales. Risks with high probability and high impact are likely to require further analysis, including quantification, and aggressive risk management.  The risk rating is accomplished using a matrix and risk scales for each risk or condition.

##### A risk’s probability scale naturally falls between 0.0 (no probability) and 1.0 (certainty). Assessing risk probability may be difficult because expert judgment is used, often without benefit of historical data. A general scale (e.g. .1/.3/.5/.7/.9), representing probabilities from very unlikely to almost certain, could be used.

The risk’s impact scale reflects the severity of its impact on the project objective. Impact scales can be ordinal or cardinal depending on the culture of the organization conducting the analysis.  Ordinal scales are simply rank-ordered values (e.g. very low, low, moderate, high and very high).  Cardinal scales can be linear (e.g. .1 / .3 / .5 / .7 / .9) but are often non-linear (e.g. .05 / .1 / .2 / .4 / .8) reflecting the organization’s desire to avoid high-impact risks. The intent of both approaches is to assign a relative value to the impact on project objectives if the risk in question occurs.  Well-defined scales, whether ordinal or cardinal, can be developed using definitions agreed upon by the organization. These definitions improve the quality of the data and make the process more repeatable. Figure 11-2 is an example of evaluating risk impacts by project objective and illustrates its use for either ordinal or cardinal approach. These scales might have been prepared by the organization before the project begins.

Figure 11-2. Rating Impacts for a Risk

| Evaluating Impact of a Risk on Major Project Objectives (Ordinal scale or cardinal, non-linear scale) |
| --- |
| Project Objective | Very Low .05 | Low .1 | Moderate .2 | High .4 | Very High .8 |
| Cost | Insignificant cost increase | < 5% cost increase | 5%-10% cost increase | 10%-20% cost increase | >20% cost increase |
| Schedule | Insignificant schedule slippage | Schedule slippage < 5% | Overall project slippage 5% - 10% | Overall project slippage 10% - 20% | Overall project schedule slips > 20% |
| Scope | Scope decrease barely noticeable | Minor areas of scope are affected | Major areas of scope are affected | Scope reduction unacceptable to the client | Project end item is effectively useless |
| Quality | Quality degradation barely noticeable | Only very demanding applications are affected | Quality reduction requires client approval | Quality reduction unacceptable to the client | Project end item is effectively unusable |

. Figure 11-3 is a Probability–Impact matrix.  It illustrates the multiplication of the probability and impact, a common way to combine these two dimensions, to determine whether a risk is considered low, moderate or high. A non-linear scale is shown for impact assessment in that Figure.  Alternatively, the P-I matrix can be developed using ordinal scales. The organization must determine which combinations of probability and impact result in a risk’s being classified as high risk (red condition), moderate risk (yellow condition), and low risk (green condition) for either approach. The risk score helps put the risk into a category that will guide risk response actions.

Figure 11-3. Probability – Impact Matrix

| Probability and Impact Score for a Specific Risk |
| --- |
| Probability | Risk Score = P x I |
| 0.9 | 0.05 | 0.09 | 0.18 | 0.36 | 0.72 |
| 0.7 | 0.04 | 0.07 | 0.14 | 0.28 | 0.56 |
| 0.5 | 0.03 | 0.05 | 0.10 | 0.20 | 0.40 |
| 0.3 | 0.02 | 0.03 | 0.06 | 0.12 | 0.24 |
| 0.1 | 0.01 | 0.01 | 0.02 | 0.04 | 0.08 |
|  | 0.05 | 0.10 | 0.20 | 0.40 | 0.80 |
|  | Impact on an Objective (e.g. cost, time, or scope) (Ratio Scale) |

.3 Project assumptions testing. Identified assumptions must be tested against two criteria: assumption stability and the impact on the project if the assumption is false.  Alternative assumptions that may be true should be identified and their impact on the project objectives tested in the qualitative risk analysis process.

.4 Data precision ranking. Qualitative risk analysis requires accurate and unbiased data if it is to be helpful to project management. Data precision ranking is a technique to evaluate the degree to which the data about risks are useful for risk management. It involves examining:

- Extent of understanding of a risk

- Data available about the risk

- Quality and integrity of data

- Reliability of data

The use of data of low precision, for instance if a risk is not well understood, may lead to a qualitative risk analysis of little use to the project manager. If a ranking of data precision is unacceptable, it may be possible to gather better data.

11.3.3 Outputs from Qualitative Risk Analysis

.1 Overall risk ranking for the project.  Risk ranking may indicate the overall risk position of a project relative to other projects by comparing risk scores.  It can be used to assign personnel or other resources to projects with different risk rankings, to make a benefit-cost analysis decision about the project, or to support a recommendation for project cancellation.

.2 List of prioritized risks. Risks and conditions may be prioritized by their group category (high, moderate, and low) at a detailed level, perhaps at the lowest WBS level. Risks may also be grouped by those that require an immediate response and those that can be handled at a later date. Cost, schedule, functionality and quality risks may be assessed separately with different ratings. Significant risks should have a description of the basis for the assessed probability and impact.

.3 List of risks for additional analysis and management. Risks classified as high or moderate would be prime candidates for more analysis, including quantitative risk analysis, and for risk management action.

11.4 Quantitative Risk Analysis

The quantitative risk analysis process aims to analyze numerically the probability of each risk and of its impact on project objectives, as well as the extent of overall project risk. This process uses techniques such as Monte Carlo simulation and decision analysis to:

- Determine the probability of not achieving a specific project objective.

- Quantify the risk exposure for the project and determine the size of cost and schedule contingency reserves that may be needed.

- Identify risks requiring the most attention by quantifying their relative contribution to project risk.

- Identify realistic and achievable cost, schedule or scope targets.

Quantitative risk analysis generally follows qualitative risk analysis.  It requires risk identification.  The qualitative and quantitative risk analysis processes can be performed separately or together.  Considerations of time and budget availability, and the need for qualitative or quantitative statements about risk and impacts will determine which method(s) to use.

11.4.1 Inputs to Quantitative Risk Analysis

.1 Risk management plan. This plan is described in 11.1.3.

.2 Identified risks.  These are described in 11.2.3.1

.3 List of prioritized risks. This is described in Section 11.3.3.2.

.4 List of risks for additional analysis and management.   This is described in 11.3.3.3

.5 Historical information. Information on prior, similar completed projects , studies of similar projects by risk specialists, and risk databases that may be available from industry or proprietary sources.

.6 Expert judgment. Input may come from the project team, other subject matter experts in the organization, and from others outside the organization. Other sources of information include engineering or statistical experts.

.7 Other planning outputs. Most helpful planning outputs are the project logic and duration estimates used in determining schedules, the WBS listing of all cost elements with cost estimates, and models of project technical objectives.

11.4.2 Tools and Techniques for Quantitative Risk Analysis

.1 Interviewing. Interviewing techniques are used to quantify the probability and impact of risks on project objectives. A risk interview with project stakeholders and subject matter experts may be the first step in quantifying risks. The information needed depends on the type of  probability distributions that will be used. For instance, information would be gathered on the optimistic, pessimistic, and the most likely scenarios if triangular distributions are used. Examples of three-point estimates for a cost estimate are shown in Table 11-4.

Table 11-4. Cost Estimates and Ranges from the Risk Interview

| Project Cost Estimates and Ranges |
| --- |
| WBS Component | Low | Most Likely | High |
| Design | 4 | 6 | 10 |
| Build | 16 | 20 | 35 |
| Test | 11 | 15 | 23 |
| Total Project |  | 41 |  |

Continuous probability distributions are usually used in quantitative risk analysis..  Distributions represent both probability and impact. Common distribution types include the uniform, normal, triangular, beta and log normal. Two examples of these distributions are shown in Figure 11-5.

Figure 11-5. Examples of Commonly-used Probability Distributions

Documenting the rationale of the risk ranges is an important component of the risk interview because it can lead to effective strategies for risk response in the risk response planning process described in Section 11.5.

.2 Sensitivity analysis. Sensitivity analysis helps to determine which risks have the most potential impact on the project. Sensitivity analysis examines the extent to which the uncertainty of each project element affects the objective being examined when all other uncertain elements are held at their baseline values.

.3 Decision tree analysis. A decision analysis is usually structured as a decision tree.  The decision tree is a diagram that describes a decision under consideration and the implications of choosing one or another of the available alternatives. It incorporates probabilities of risks and the costs or rewards of each logical path of events and future decisions. Solving the decision tree indicates which decision yields the greatest expected value to the decision-maker when all the uncertain implications, costs, rewards and subsequent decisions are quantified. A decision tree is shown in Figure 11-6..

Figure 11-6. Decision Tree Analysis xxx

.4 Simulation. A project simulation uses a model that translates the uncertainties specified at a detailed level into their potential impact on objectives that are expressed at the level of the total project.  Project simulations are typically performed using the Monte Carlo technique.

For a cost risk analysis, a simulation may use the traditional project WBS as its model. For a schedule risk analysis, the Critical Path Method (CPM) schedule is used. A cost risk simulation result is shown in Figure 11-7.

Figure 11-7. Cost Risk Simulation .xxx

11.4.3 Outputs from Quantitative Risk Analysis

.1 Prioritized list of quantified risks. This list of risks includes those posing the greatest threat or present the greatest opportunity to the project together with a measure of their impacts.

.2 Probabilistic analysis of the project.  Forecasts of potential project schedule and cost results listing the possible completion dates or project duration and costs with their associated confidence levels.

.3 Probability of achieving the project cost and time objectives. The probability of achieving the project objectives under the current plan and with the current knowledge of the risks facing the project can be estimated using qualitative risk analysis. .

11.5 Risk Response Planning

Risk response planning is the process of developing options and determining actions to enhance opportunities and to reduce threats to the project’s objectives. It includes the identification and assignment of individuals or parties to take responsibility for each agreed risk response. This process ensures that identified risks are properly addressed. The effectiveness of response planning will directly determine whether risk increases or decreases for the project.

Risk response planning must be appropriate to the severity of the risk, cost-effective in meeting the challenge, timely to be successful, realistic within the project context, agreed upon by all parties involved and owned by a responsible person.  Selecting the best risk response from several options is often required.

11.5.1	Inputs to Risk Response Planning

.1 Risk management plan. This plan is described in 11.1.3.

.2 List of prioritized risks from qualitative risk analysis. This is described in 11.3.3.2

.3 Overall risk ranking of the project.  This is described in 11.3.3.1.

.4 Prioritized list of quantified risks from quantitative risk analysis.. This is described in 11.4.3.1.

5. Probabilistic analysis of the project.  This is described in 11.4.3.2.

6. Probability of overrunning the project cost and time objectives.   This is described in 11.4.3.3

.7 List of potential responses.  In the risk identification process, actions may be identified that respond to individual risks or categories of risks.

.8 Risk thresholds. The level of risk that is acceptable to the organization will influence risk response planning.

.9 Risk owners. A list of project stakeholders able to act as owners of risk responses.  Risk owners should be involved in developing the risk responses.

.10 Common risk responses. Several risks may be driven by a common cause. This situation may reveal opportunities to mitigate two or more project risks with one generic response.

11.5.2	Tools and Techniques for Risk Response Planning

Several risk response strategies are available (see sections 11.5.2.1 to 11.5.2.4).  The strategy that is most likely to be effective should be selected for each risk.   Then, specific actions should be developed to implement that strategy. Primary and backup strategies may be selected.

.1 Avoidance. Risk avoidance is changing the project plan to eliminate the risk or condition or to protect the project objectives from its impact. The project team can never eliminate all risks, but some specific risks may be avoided.

Some risk causes that arise early in the project can be dealt with by clarifying requirements, obtaining information, improving communication, or acquiring expertise. Reducing scope to avoid high-risk activities, adding resources or time, adopting a familiar approach instead of an innovative one, or avoiding an unfamiliar subcontractor may be examples of avoidance.

.2 Transfer. Risk transfer is seeking to transfer the impact of a risk to a third party together with ownership of the response. Transferring the risk does not eliminate it, but simply gives another party responsibility for its management.

Transferring liability for risk is most effective in dealing with financial risk exposure. Risk transfer nearly always involves payment of a risk premium to the party taking on the risk. It includes the use of insurance, performance bonds, warranties and guarantees. Contracts may be used to transfer liability for specified risks to another party. Use of a fixed price contract may transfer risk to the seller if the project’s design is stable. A cost reimbursable contract leaves more of the risk with the buyer, but it may help reduce cost if there are mid-project changes.

.3 Mitigation. Mitigation seeks to reduce the probability and/or impact of a risk to below an acceptable threshold. Taking early action to prevent a risk from occurring is more effective than trying to repair the consequences after it has occurred. Mitigation costs should be appropriate given the likely impact and probability of the risk.

Risk mitigation may take the form of implementing a new course of action that will reduce the problem, e.g. adopting less complex processes, conducting more seismic or engineering tests, or choosing a more stable supplier. It may involve changing conditions so that the probability of the risk occurring is reduced, e.g. adding resources or time to the schedule. It may require prototype development to reduce the risk of scaling up from a bench scale model.

Where it is not possible to reduce probability, a mitigation response might address the risk impact by targeting linkages that determine the impact severity. For example, designing redundancy into a subsystem may reduce the impact that results from a failure of the original component.

.4 Acceptance. This technique indicates that the project team has decided not to change the project plan to deal with a risk or are unable to identify any other suitable response strategy. Active acceptance may include developing a contingency plan to execute should a risk occur. Passive acceptance requires no action, leaving the project team to deal with the risks as they occur.

A contingency plan is most useful for risks that may arise during the project.  Developing a contingency plan in advance can greatly reduce the cost of an action should the risk occur.  Risk triggers, such as missing intermediate milestones, should be defined and tracked.

A fallback plan is developed if the risk has a high impact or if the selected strategy may not be fully effective.  This might include allocation of a contingency amount, development of alternative options or changing project scope.

The most usual risk acceptance response is to establish a contingency allowance, or reserve, including amounts of time, money or resources to account for known risks. The allowance should be determined by the impacts, computed at an acceptable level of risk exposure, for the risks that have been accepted.

11.5.3 Outputs from Risk Response Planning

.1 Risk response plan. The risk response plan should be written to the level of detail at which the actions will be taken.  It should include some or all of the following:

- Identified risks, their description, the area of the project (e.g. WBS element) affected, their causes and how they may affect project objectives.

- Risk owners and assigned responsibilities.

- Results from the qualitative and quantitative risk analysis processes.

- Agreed responses including avoidance, transference, mitigation or acceptance for each risk in the management plan.

- The level of residual risk expected to be remaining after the strategy is implemented.

- Specific responses to implement the chosen strategy.

- Budget and times for responses.

- Contingency plans and fallback plans.

.2 Residual risks. Residual risks are those that remain after avoidance, transfer or mitigation responses have been taken. They also include minor risks that have been accepted and addressed, e.g. by adding contingency amounts to the cost or time allowable.

.3 Secondary risks. Risks that arise as a direct result of implementing a risk response are termed secondary risks. These should be identified and responses planned for.

.4 Contractual agreements. Contractual agreements may be entered into to specify each party’s responsibility for specific risks, should they occur, and for insurance, services, and other items as appropriate in order to avoid or mitigate threats.

.5 Contingency reserve amounts needed. The probabilistic analysis of the project (11.4.3.2) and the risk thresholds (11.5.1.8) help the project manager determine the amount of buffer or contingency needed to reduce the risk of overruns of project objectives to a level acceptable to the organization.

.6 Inputs to other processes. Most responses to risk involve expenditure of additional time, cost or resources and require changes to the project plan. Organizations require assurance that spending is justified for the level of risk reduction. Alternative strategies must be fed back into the appropriate processes in other knowledge areas.

.7 Inputs to a revised project plan incorporating risk responses.  A new plan will require further risk management, which is an iterative process.

11.6 Risk Monitoring and Control

Risk monitoring and control is the process of keeping track of the identified risks, monitoring residual risks and identifying new risks, ensuring the execution of risk plans and evaluating their effectiveness in reducing risk. Risk monitoring and control records risk metrics that are associated with implementing contingency plans. Risk monitoring and control is an ongoing process for the life of the project. The risks change as the project matures, new risks develop or anticipated risks disappear. Good risk monitoring and control processes provide information that assists with making effective decisions in advance of the risks occurring.  Communication to all project stakeholders is needed to assess periodically the level of risk to the project.

The purpose of risk monitoring is to determine if:

- Risk responses have been implemented as planned.

- Risk response actions are as effective as expected or if new responses should be developed.

- Project assumptions are still valid or strongly held.

- Risk exposure has changed from its prior state, with analysis of trends.

- A risk trigger has occurred.

- Proper policies and procedures are followed.

- Risks have occurred or arisen that were not previously identified.

Risk control may involve choosing alternative strategies, implementing a contingency plan, taking corrective action, or re-planning the project. The risk owner should report periodically to the project manager and the risk team leader on the effectiveness of the plan, any unanticipated effects and any mid-course correction needed to mitigate the risk.

11.6.1 Inputs to Risk Monitoring and Control

.1 Risk management plan.  The risk management plan is described in 11.1.3.

.2 Risk response plan. The risk response plan is described in 11.5.3.1.

.3 Project communication. Work results and other project records described in 10.3.1 provide information about project performance and risks. Reports commonly used to monitor and control risks include Issues Logs, Action Item Lists, Jeopardy Warnings, or Escalation Notices.

.4 Additional risk identification and analysis. As project performance is measured and reported, potential risks not previously identified may surface.  The cycle of risk identification, assessment, quantification and response planning should be implemented for these risks.

.5 Scope changes.  Scope changes often require new risk analysis and  response plans.  Scope changes are described in 5.5.3.1.

11.6.2 Tools and Techniques for Risk Monitoring and Control

.1 Checklists. Checklists used in risk identification may also be used in monitoring and controlling risk. Care must be taken to explore items that do not appear on a standard checklist if they seem relevant to the specific project.

.5 Project audits. Risk auditors examine and document the effectiveness of the risk response planning in preventing, transferring or mitigating risk occurrence as well as the effectiveness of the risk owner. Risk audits are performed during the project life cycle to control risk.

.2 Periodic project risk reviews. Project risk reviews should be regularly scheduled. Project risk should be an agenda item at all team meetings. Risk ratings and prioritization may change during the life of the project. Any changes may require additional qualitative or quantitative risk analysis.

.3 Earned value analysis. Earned value is used for monitoring overall project performance against a baseline plan.  Results from an earned value analysis may indicate potential deviation of the project at completion from cost and schedule targets.  When a project deviates significantly from the baseline, updated risk identification, assessment and quantification should be performed.  Earned value analysis is described in Section 10.3.2.4.

.4 Technical performance measurement.  Technical performance measurement compares technical accomplishments during project execution to the project plan’s schedule of technical achievement.   Deviation, such as not demonstrating functionality as planned at a milestone, can imply a risk to achieving the project’s scope.

.5 Additional risk response planning. If a risk emerges that was not anticipated in the risk response plan, or its impact on objectives is greater than expected, the planned response may not be adequate. It will be necessary to perform additional response planning to control the risk.

    - Outputs from Risk Monitoring and Control

.1 Workaround plans. Workarounds are previously unplanned responses to emerging risks. Workarounds must be properly documented and incorporated into the project plan and risk response plan.

.2 Corrective action. Corrective action consists of performing the contingency plan or workaround.

.3 Project change requests. Implementing contingency plans or workarounds frequently results in a requirement to change the project plan to respond to risks. The result is issuance of a change request that is managed by overall change control as described in Section 4.3.

.4 Updates to the risk response plan. Risks may occur or not. Risks that do occur should be documented and evaluated. Implementation of risk controls may reduce the impact or probability of identified risks. Risk rankings must be reassessed so that new, important risks may be properly controlled.  Risks that do not occur should be documented and closed in the risk response plan.

.5 Risk database. A repository that provides for  collection, maintenance and analysis of data gathered and used in the risk management processes.  Use of this database will assist risk management throughout the organization and over time and form the basis of a  lessons learned program.

.6 Updates to risk identification checklists.

# Text boxes

Beta Distribution

Triangular Distribution

12%

$41

$49.92